## Slide 1
Discussion Outline
RFID Tag-Encoding Blue Book updates to respond to CESG RIDs
  KKG observations and suggestions re: Peter Shames, SANA registries
    ISS background comment; SANA registries
    CCSDS Registry Policy Management draft and current CCSDS OID
    PICS statement
  ObjectID namespace architecture
    Stakeholder INPUTS (ISS, OC, EV, RSA, etc.)
  16-bit ObjectID namespace migration to 24-bit (for a 96-bit tag): ObjectID namespace will remain backwards compatible; BUT
  Migration to an EPC-compliant namespace deprecates the current ISS namespace in favor of a fully EPC-compliant definition (we could provide translation at the application-layer software as observed previously)
HDR WLAN stakeholder engagement strategic brainstorming
  Purpose  Scope, stakeholders (someone with an interest in the outcome), users, communication architects and engineers
  Whitepaper?
  What about casting problem as a Roadmap activity? (HDR WLANs in support of space-agency Exploration activities; PSCR LBS Roadmap ex.)
FY2016 activities
  Expected activity definitions (deliverables) and timeline

## Slide 2
NASA NNJ15HE05P FY2016 Milestones
Monthly Telecon
Support
Biannual
International
Meeting Support
Additional
Support
Activities
FY2016 Milestones
1. Deliverable: FY2016: Wireless Working Group, WWG, Monthly Meeting Support
Deliverable: CCSDS RFID Tag Encoding Blue Book FINAL Draft for publication: 15-Oct-2015
Deliverable: CCSDS Fall 2015 Meeting Support Darmstadt, Germany: 09-Nov-2015  13-Nov-2015
Deliverable: CCSDS High Data Rate WLAN Blue Book Roadmap: 01-Dec-2015
Deliverable: CCSDS Spring 2016 Meeting Support Cleveland, OH USA: 04-Apr-2016  08-Apr-2016
Deliverable: CCSDS High Data Rate Blue Book outline and organization initial draft: 15-Apr-2016
Deliverable: CCSDS High Data Rate Blue Book 1st Draft: 15-Sep-2016
Dec
2015
Jan
2016
Feb
2016
Mar
2016
Apr
2016
May
2016
Jun
2016
Jul
2016
Aug
2016
Sep
2016
2015 Fall Meeting
Darmstadt, Germany
09-13 Nov-2015
RFID Tag Encoding
Blue Book FINAL for publication
15-Oct-2015
High Data Rate WLAN
Blue Book initial draft
15-Sep-2016
Oct
2015
Nov
2015
2016 Spring Meeting
Cleveland, OH USA
04-08 Nov-2016
High Data Rate WLAN
Blue Book Roadmap
01-Dec-2015
High Data Rate WLAN
Blue Book outline & organization initial draft
15-Apr-2016
Notes: Planning Notes 11-Mar-2013:
Discuss SABL Project Plan with Shea and Louis
Coordinate dates for RSA 2FA TIM at HOSC (Shea, Jim, Shankini); cost share this trip with BioServe
Determine timeline on DTN2 Simulator – coordinate HOSC DTN2 G/W testing, test plan, with the HOSC
Will need to plan Automation support for additional BioServe SABL tasks
Have an IDSCam close-out sprint; can transition to SABL early as necessary
HOSC RSA 2FA meeting this week and travel coordination

## Slide 3
  WWG RFID Encoding Blue Book:
  Spring 2015: Final draft#2 RFID Encoding Blue Book [completed]
  Release to Area Director [completed]
  Submission to Secretariat
  Fall 2015: Final Agency review completion
  First/second prototype development completion
  Spring 2016: CMC approval
  WWG Wireless Local Area Network Blue Book:
  Spring 2015: Initiation of standardization specification
  Fall 2016: Final draft#1 WLAN Blue Book
  Spring 2018: Final draft#2 WLAN Blue Book
  Release to Area Director
  Spring 2019: Final Agency review completion
  Fall 2020: First/second prototype development completion
  Winter 2020: CMC approval
SOIS (WWG) Area Report to CESG, Spring 2015
Notes: 3