## Sheet1
Status | Assignee | SOIS Wireless WG -Task Description
Last Updated: February 12, 2009
General Items
| Magenta book contributors | Review CCSDS Magenta Book recommended outline; align with "our" proposed RFID Magenta Book outline. A Magenta Book has a much broader scope across CCSDS and most of the "template" Magenta Book sections will need to be addressed. Is there a very good Magenta Book to gain insight from as well? Answer: There is no Magenta Book outline that we need to follow; Our Magenta Books will reference the WWG Green Book for basic technical information, will concentrate on a specific domain of application (RFID, Intra-spacecraft, AIT) with detailed use cases and specific protocol recommendations and perhaps with recommended application profiles.
| Kevin, Larry | Determine if we need to address bridging (layer-2) of wireless networks
| Kevin | Are application services part of the purview of the Wireless Working Group - or is this at a higher level in the stack; or should we include generalized services that the link-layer provides for wireless such as connection-oriented, datagram oriented, support IP, support QoS, support Security (comm. services vs. app services); look at IEEE 802.11, 802.15, 802.16 specifications. Application services are the domain of SOIS-PnP.
| Kevin | Read Peter Shames protocol and architecture development best practices documents - may want to post on CWE
| Kevin | Note: Stuart's DVS Red Book is very service oriented as an observation; I liked the (informative) and (descriptive) tags for the different sections
| Kevin | Do we want a hyperlink in the document to point to an online list of missions that have used the technology or standard? (I like this idea; maybe just need to kick the effort off for SOIS, BioNet, and DTN)
| Kevin | Talk with Tom Gannon concerning copyrighted images/diagrams guidelines (this important issue was brought up by Jean-Francios)
| Kevin | Compose a first-cut activity roadmap and iterate with group with regards to Magenta Books and future activities - do mile Automation milestones
| Kevin | Forward draft Green Book to Tom Gannon for early feedback
| As applicable | Can we get real data to address EMI concerns with measurements - lots of activities (ISS, Shuttle, aircraft, wireless-on-launch) to draw from
| All, Kevin lead | Wireless in spacecraft is not so rare - document actual mission activities in the Green Book - this is similar to the online list of missions concept
| As applicable | Include Modeling and Performance simulations as appropriate in Annexes (this is a CCSDS Systems Engineering area topic)
| As applicable | Possibly use application profiles as an accompanying reference; Peter Shames likes application profiles - look at baseline architecture (Annex)
| Pat, Kevin | COTS verbiage (trade-offs) in Appendix; mention in introduction?
Questions to review with Group
Format of Table 3.4? As Pat suggested (a simplified table with full-fledge detailed table in an Annex)? As I like? With my desired updates?
We can release to NASA and complete references, glossary, etc as a potential strategy
JSC-EV's suggested final completion items:
1. Paragraph regarding the importance of standards in wireless systems (I have this in my paper with Stephen Braham)
a) Derive for Whitepaper
b) Tie to spin-in-vs. spin-out
2. Rewrite (maybe replace or omit) the cavity propagation section
3. Replace RF band desiginations in Annex with IEEE Standard band nomenclature
4. Discuss table: as is / omit / modify
| Kevin | Ensure all diagrams and figures that were not composed by the group are properly referenced
| Kevin | Ensure strict compliance with CCSDS Publications specifications
| Kevin | Ensure references in Green Book meet CCSDS Publications specifications
Green Book Updates - Q&D
| Kevin | Look into status of 802.22 and 802.27 (combination of 802.11 and 802.16): Possibly categorize as standardization efforts to monitor
| Jean Francios | Add verbiage noting effects of particulates for IR wireless
Green Book Updates - medium
| Kevin | Table 3.4: consider adding MAC protocol-oriented services to summary table or create a second table (connection-oriented, QoS, security, etc); e.g., Bluetooth isochronous data support
| Kevin, Larry | Verbiage explaining packet-based and frame-based (in case of base station) network emphasis (802.16 references?)
Green Book Updates; general topics to overview
| Kevin | 2.5.1 Overview of Quality of Service capabilities and concerns with wireless (C3I requirements?)
| Kevin | 2.5.2 Overview of generalized security concerns for wireless; ensure meets CCSDS requirements for a Green Book security section (C3I reqts?)
| Cathy | 3.5 Compose space-main RF Spectrum Planning Section
Final items to ensure are complete
| Kevin | Set English as default language for entire document and spell-check
| Kevin | Ensure all Figures properly referenced from the numeric identification perspective in the text of the Green Book
| Kevin | All acronyms in Annex A
| Kevin | Update Glossary of Terms
Magenta Book Strategies
| Kevin | Magenta Book does not have a pre-defined format; we can tailor to our perceived needs; but need to make recommendations
| Kevin | Create initial WWG Use Case Compendium and post
| Lester | 4.5 AIT Planetary protection use case scenario
| Eric | A seismology sensor network seems like a very nice use case - can we add?
| Annette, Sev | More AIT scenarios / use cases
| Kevin | Pat's RFID slides for the ISS DTO; Eric's planetary wireless scenarios
| All | Review the Lunar Surface Wireless Communications and Navigation presentations for incorporation of material as Use Cases in Magenta Books
| Eric | Include planetary wireless scenarios
Incorporate Jim Schier's Wireless Workshop diagrams as appropriate (coordinate with Pat Fink); M. Tossaint's WiMax topologies diagram
| Larry | Updated Planetary surface communication scenario for inclusion in the Use Case Compendium
SOIS and SLS Wireless WG coordination
Suggest using the current WWG Green Book as the single-point source over viewing technologies, standards and use cases for both groups
Specific strategy to decompose the Wireless Green Book into modular sections (Do some forward work in this regard)
Although there will be protocols and application overlap across the functional domains, the two groups shall ensure consistency of efforts
One area that must be addressed is which group has primary responsibility for networks that have cross functional domains of application
Show path forward in terms of documents produced by both groups in Green Book
State individual WG functional domains, application areas, and Magenta Books track
BioNet will bridge across both wireless networks
Suggest common Working Group meeting at the Spring and Fall conferences
Will want to form relationship with SIS to ensure desired network functionality and wireless bridging
SLS Wireless WG: Include Table 3.4 from the WWG Green Book as initial concept for Working Group responsibilities
Intra-vehicle, proximity networks (RFID, WLAN, WPAN) are domain of SOIS (short-range, less than 200 m)
Inter-vehicle, surface-to-surface, surface-to-orbiter (TC/TM, Prox-1, WMAN) are domain of SLS (long-range up to several kilometers)
A standard for a "technology" is much easier to bound than a standard for an "application" area
Where do spectrum issues get resolved?
What is the level of flexibility required is always an important question; greater flexibility necessitates more complex protocols
Completed Action Items
2008-10-14 | Ben | Talk to the CCSDS System Engineering Group concerning wireless modeling support and advice
2008-10-17 | Kevin | Coordinate with Jean-Luc Gerner, Chris Taylor, Adrian Hooke concerning SLS Wireless BoF formation
404983 | Kevin | Create a wireless-core mail list for core group member discussions outside of sois-wir list (Joining requires moderator approval)
2008-10-22 | Kevin | Remove the Groundside Inventory Control reference from the WWG Charter
2008-10-29 | Kevin | Ensure Ben Ballard has a CWE login
2008-11-03 | Pat | Set up Telecon phone information; set up a NASA International meet-me phone number
v082c | Kevin | Eliminate duplicate title entries in Table of Contents
v082c | Kevin | Ensure all Figures are properly captioned and in Table of Contents
v083 | Philippe | 802.15.3 WiMedia one-pager
v083 | Larry, Adam | 802.16 WMAN overview (Adam to review Larry's write-up)
v086 | Jean Francios | 2.4.7 Review and update of optical communications section
v087 | Kevin | All three Magenta books are part of a series - put in Green Book Introduction
v087 | Kevin | 2.4.3 Add verbiage for the overview section that specific technology inclusion (e.g., ISO, EPCglobal) does not constitute an endorsement
v087 | Kevin | 2.4.3 State alignment of EPCglobal Class 1 Gen 2 standard with ISO 18000-6
v087 | Kevin | 2.4.3 Need to back up statement that RuBee fills gap between RFID and 802.15.4 networks (essentially I believe this is from the mesh perspective)
v087 | Kevin | 2.4.4 ZigBee is just one particular 802.14.5 network stack implementation
v087 | Kevin | 2.4.4.1 Specifically the Bluetooth 2.0 standard
v087 | Kevin | 2.5.3 Eliminate the voice and video coding section
v087 | Kevin | Figure 2-13 (11 channels in US; 14 channels in a few other countries; just add some verbiage to Fig. 2-13)
v087 | Kevin | 3.6 Auxiliary Concepts : Probably just delete the section
v087 | Kevin | Replace "lunar" and "martian" with planetary where appropriate
v088 | Kevin | Contains Kevin's and Jean-Francois' updates prior to adding JSC updates; has all of the Use Cases still in Chapter 4 including extra ESA use cases
v090 | JSC, Kevin | Contains all of the JSC updates from (RJB+AMS+RW+PF_v7) in "raw" form for review to contributors if necessary
v093 | Kevin | All JSC updates (RJB+AMS+RW+PF_v7) with document layout, Table of Contents, Table of Figures, and Table of Tables updated properly
v093 | Rick | Rick's RFSaw graphics inclusion
v093 | Removed | 2.3.4 Verbiage stating assumptions on generalized transmission range characteristics for ISM band
v093 | Pat, Rick | 2.4.3.1 Compose section on SAW-based RFID tags
v093 | Rick, Pat | 2.3.4 Verbiage concerning unlicensed spectrum (U.S. ISM bands) availability in non-US areas
v093 | Rick | 2.4.5 802.11a / g is OFDM; 802.11n is MIMO
v094 | Kevin | Figures properly enumerated and properly referenced in the text; all figures and tables in proper order in Table of Figures / Table of Tables
v095 | Kevin | Put all of the Chapter 4 Use Cases in their own Document to ultimately incorporate into our Magenta Books (WWG Use Cases); post on CWE
v096 | Kevin | 2.3.6.3 Add verbiage detailing Boltzmann's constant concerning thermal noise
v096 | Kevin | Check on current status of IEEE 1902.1 RuBee standard uptake - the jury is still out; let's monitor over the next year
v097 | Eric | 3.3 Compose EMI/EMC section
v102 | Kevin | 2.3.6.5 Better diagram; highlight radio transmission; add A/D D/A; a proper radio model would be best here
v102 | Kevin | 2.3.6.6 Diagrams on FM, AM, PM modulation; noise immunity of FM over AM
v102 | Kevin | 2.3.6.7 Noise immunity advantages of spread spectrum techniques: DSSS, FHSS, OFDM with diagrams